## Sheet1
|  |  |  | Sep | Oct | Oct | Oct | Oct | Nov | Nov | Nov | Nov | Dec | Dec | Dec | Dec | Dec | Jan | Jan | Jan | Jan | Feb | Feb | Feb | Feb | Mar | Mar | Mar | Mar | Mar | Apr | Apr | Apr
|  |  |  | 30 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20
1a Data Exploration
| 1a.1 | Document of Table Descriptions | bar: Sep 30 to Oct 14
| 1a.2 | Creation of Data Mapping | bar: Oct 7 to Oct 21
| 1a.3 | More Descriptive Data Dictionary | bar: Oct 7 to Nov 4
|  | 1a.3.1 | Univariate Distributions | bar: Oct 14 to Nov 4
|  | 1a.3.2 | Identify Target Variable | bar: Oct 14 to Nov 4
|  | 1a.3.3 | Identify Missingness | bar: Oct 14 to Nov 4
1b Business Understanding
| 1b.1 | Contact IAA Person | bar: Sep 30 to Oct 7
| 1b.2 | Contact Doctor | bar: Sep 30 to Oct 7
| 1b.3 | Identify Claim Codes | bar: Oct 14 to Oct 21
2 Data Preparation
3 Midterm Report
4 Model Building
5 Model Assessment
6 Final Report